## Test Summary Report
Project Overview
Project Name: | Bellevue College
Module/Item Name: | Student Central Form
Version | 1
Project Type | Testing and Verification
Start Date | 2018-09-19
End Date | 43363
Created By | Pavani Cherukuri
Test Summary Report
Test Types | Test Cases Planned | Test Cases Executed | Test Cases Passed | Test Cases Failed
Functional | 10 | 10 | 7 | 3
Non-Functional and exploratory | 5 | 5 | 5 | 0

## Tracebality Matrix
Project Overview
Project Name: | Bellevue College
Module/Item Name: | Student Central Form
Version | 1
Project Type | Testing and Verification
Start Date | 2018-09-19
End Date | 43363
Created By | Pavani Cherukuri
Use-Case ID | Use-Case Description
UC_ID 01 | Launching of Student Central Request Form
UC_ID 02 | Entering Input Values
UC_ID 03 | Submission of Ticket
Tracebility Matrix
|  | Test Case ID | TC_ST_1 | TC_ST_2 | TC_ST_3 | TC_ST_4 | TC_ST_5 | TC_ST_6 | TC_ST_7 | TC_ST_8 | TC_ST_9 | TC_ST_10 | TC_ST_11 | TC_ST_12 | TC_ST_13 | TC_ST_14 | TC_ST_15
Use-Case ID
UC_ID 01 | bar: TC_ST_1; Tracebility Matrix TC_ST_11 to Tracebility Matrix TC_ST_15
UC_ID 02 | bar: Tracebility Matrix TC_ST_2 to Tracebility Matrix TC_ST_8; Tracebility Matrix TC_ST_13
UC_ID 03 | bar: Tracebility Matrix TC_ST_9 to Tracebility Matrix TC_ST_10

## Test Case
UC_ID | TC_ID | Test Description | PreCondition/ Pre requisite | Steps | Test Data | Expected Result | Actual Result | Status | Defect ID | Comments
UC_ID #01 | TC_ST_001 | Verify the launch of the form | URL of the Student Central page should be available | Select the URL of the student central | URL: https://forms.bellevuecollege.edu/test-form/test.php | The Student Central Request page should be displayed in the web browser | The Student Central Request Page is displayed in the web browser | Pass
UC_ID #02 | TC_ST_002 | Verify the input fields Name is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Enter values into Name field | 1. Test 2. Space bar and special characters 3. 0-9 4. combination of Alphabets, Numbers and special values 5. BVA- maxium- unknown Min-1 6. Null values | The input field- Name should be dispalyed and accepting values. In case of Null values or spaces appropriate message should be displayed | The Name field is displayed in Student Central Requests page and on entering null or empty spaces error message is being displayed while submission of the form | Pass |  | Error messages can be more customised and right fields should be highlighted and refereshed for entering new values
UC_ID #02 | TC_ST_003 | Verify the input fields Student Id is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Enter values into StudentId field | 1. Test 2. Space bar and special characters 3. 0-9 4. combination of Alphabets, Numbers and special values 5. BVA- maxium- unknown Min-1 6. Null values | The input field- StudentId should be dispalyed and accepting values. In case of Null values or spaces appropriate message should be displayed | The StudentId field is displayed in Student Central Requests page and empty spaces no error message is being displayed while submission of the form | Fail | DF_ID #01, DF_ID #02 | Error messages can be more customised and right fields should be highlighted and refereshed for entering new values
UC_ID #02 | TC_ST_004 | Verify the input fields Email Address is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Enter values into Email Id field | 1. Test.test@outlook.com 2. Space bar and special characters 3. 0-9 4. combination of Alphabets, Numbers and special values 5. BVA- maxium- unknown Min-1 6. Null values | The input field- Email Id should be dispalyed and accepting values in XXX@XXX.XXX. In case of Null values, spaces appropriate message should be displayed | The Email Id field is displayed in Student Central Requests page and on entering null or empty spaces error message is being displayed while submission of the form but mail id is accepted in below format: test@org | Fail | DF_ID #03 | Error messages can be more customised and right fields should be highlighted and refereshed for entering new values
UC_ID #02 | TC_ST_005 | Verify the input fields Subject is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Enter values into Subject field | 1. Test 2. Space bar and special characters 3. 0-9 4. combination of Alphabets, Numbers and special values 5. BVA- maxium- unknown Min-1 6. Null values | The input field- Subject should be displayed and accepting values. In case of Null values, spaces appropriate message should be displayed | The Subject field is displayed in Student Central Requests page and on entering null or empty spaces error message is being displayed while submission of the form | Pass |  | Error messages can be more customised and right fields should be highlighted and refereshed for entering new values
UC_ID #02 | TC_ST_006 | Verify the input fields Description is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Enter values into description field | 1. Test 2. Space bar and special characters 3. 0-9 4. combination of Alphabets, Numbers and special values 5. BVA- maxium- unknown Min-1 6. Null values | The input field- Description should be displayed and accepting values. In case of Null values, spaces appropriate message should be displayed | The Description field is displayed in Student Central Requests page and on entering null or empty spaces error message is being displayed while submission of the form | Pass |  | Error messages can be more customised and right fields should be highlighted and refereshed for entering new values
UC_ID #02 | TC_ST_007 | Verify the input fields Service area is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Select the displayed values in Service area drop down | 1. Select displayed values 2. Try entering data from key board or through touch pad | The input field- Service area should be displayed and dispalying and accepting values. In case of Null values appropriate message should be displayed | The input field- Service area is displayed and dispalying and accepting values. In case of Null values appropriate message are displayed while submission of the forms | Pass |  | As Service Area is a mandatory field * mark should be displayed in UI after the field name.
UC_ID #02 | TC_ST_008 | Verify the input fields Issue Category is dispalyed and accepting values | URL of the Student Central page should be available and page displayed in browser | Select the displayed values in Issue Category area drop down | 1. Select displayed values 2. Try entering data from key board or through touch pad | The input field- Issue Category should be displayed and dispalying and accepting values. In case of Null values appropriate message should be displayed | The input field- Issue Category is displayed and dispalying and accepting values. In case of Null values appropriate message are displayed while submission of the forms | Pass
UC_ID #03 | TC_ST_009 | Verify the Submit button is enabled and displayed | URL of the Student Central page should be available and page displayed in browser | Enter the above fields and click on submit | Select Submit | On Selection of submit button it should check all the required fields have input and then process the request else appropriate messages have to be displayed and fields are to be highlighted for user to input values. | On Selection of submit button the required fields have input is being checked else appropriate messages are being displayed but all fields are not being highlighted in order. | Fail | DF_ID #04
UC_ID #03 | TC_ST_010 | Verify the Submit button is displaying correct page when transaction is sucessful | URL of the Student Central page should be available and page displayed in browser | Enter all the fields and click on submit button | Name:Test StudentID: Test123 Email Id: Test@test.edu Subject:Test Description:Test Service Area: Enrollment Issue Area: Others and click on submit button | On selecing Submit button after input values are entered the resultant page should be display correct message along with other links. | On selecing Submit button after input values are entered the resultant page displays a Thank you message along with other links. | Pass
UC_ID #01 | TC_ST_011 | Verify if the URL can be accessed from Chrome, IE, Safari browsers | URL of the Student Central page should be available and page displayed in browser | Select or copy and paste URL in Chrome, IE and Safari Browser | URL: https://forms.bellevuecollege.edu/test-form/test.php | The URL should be accessed from Chrome, IE, Safari browsers | The URL is accessible from Chrome IE-10, Safari Browser | Pass
UC_ID #01 | TC_ST_012 | Verify if number of users can try to acess the Student Central Request page at the same time | URL of the Student Central page should be available and page displayed in browser | Access the Student central request page from different systems and submit data at same time as different users | Acess Student central Request page on 5 systems at same time in different browsers and submit data at same time | Student central request page should be displayed on different systems and should be able to accept data and submit data at same time from different users | Student central request page is displayed on different systems and able to accept data and submit data at same time from different users | Pass
UC_ID #01 UC_ID #02 | TC_ST_013 | Verify if the fields are displayed with user promptness for disabled people. | URL of the Student Central page should be available and page displayed in browser | Select fields dispalyed in the field |  | Verify if the fields are displayed with user promptness for disabled people. | On entering wrong data error messages are displayed |  |  | Accessibility testing for diabled people
UC_ID #01 | TC_ST_014 | Verify if other Links are displayed and accesible from Student Central Page | URL of the Student Central page should be available and page displayed in browser | Acess the other links dispalyed on the page | Click on Search, Home, Classes, Programs of study, Enrollment,Services, Campus life and other links displayed on the page | The other links should be displayed on the page and on selecting them will display resultant link | The other links are displayed on the page and on selecting them are displaying resultant page | Pass
UC_ID #03 | TC_ST_015 | Verify that session tokens are only delivered over HTTPS | URL of the Student Central page should be available and page displayed in browser | Acess the Student central request page and try manipulating the URL | Manipulate the URL | On manipulation of URL the resultant page must display appropriate error message | On manipulating URL appropriate error message are displayed along with 404 page not found page. | Pass

## Defect Report
Defect_Id | Defect Description | Steps to reproduce | Severity | Priority | Status | Created By | Assigned To | Screenshots | Comments
DF_ID #01 | Student Id field is accepting spaces | Enter spaces in Student ID field as input and related values in other fields 1. Name: Test 2. StudentID: Press space bar for couple of times 3. Email Address: test@test.com 4. Subject: test 5. Description: test 6. Service area: Enrollment Services 7. Issue category: Other 8. Press Submit Button | Medium | Medium | Open | Pavani
DF_ID #02 | Name field is getting refereshed when null values are entered in Student Id field | Enter null in Student ID field as input and related values in other fields 1. Name: Test 2. StudentID: leave it blank 3. Email Address: test@test.com 4. Subject: test 5. Description: test 6. Service area: Enrollment Services 7. Issue category: Other 8. Press Submit Button | Low | Low | Open | Pavani
DF_ID #03 | Email Field is accepting mail address in wrong format | Enter Mail id as : test@org instead of test@outlook.org | Medium | Medium | Open | Pavani
DF_ID #04 | On selecting Submit button Wrong fields are being highlighted for corrections | Enter all details apart from Service area and submit wrong fields are highlighted for entering the data | Medium | Medium | Open | Pavani